## Bedgel (Role A)
DealerOps Sprint 1 — Bedgel Fadhil Ndam Woukouo — Web
Task | Priority | Status | Planned start | Planned due | Planned hours | Actual start | Actual completion | Actual hours | Requirement and evidence notes
Review core and extension routes; record a route checklist and scope discrepancies | High | Not Started | 2026-10-12 | 2026-10-13 | 3 |  |  |  | Scope baseline; VIN/LEAD/WO/AUTH/IMG
Walk admin, bound and unbound access with email, username and phone sign-in; record outcomes | High | Not Started | 2026-10-14 | 2026-10-15 | 3 |  |  |  | AUTH-01/03/08/11/12/17; screenshots and Jira pass/fail outcomes
Create, edit, search and filter vehicles; record field and VIN outcomes | High | Not Started | 2026-10-16 | 2026-10-17 | 3 |  |  |  | DMS-01/03/05/07
Sell a vehicle; record paired-field, sold-lock and audit outcomes | High | Not Started | 2026-10-19 | 2026-10-20 | 3 |  |  |  | DMS-08/10/11/14
Walk customer create, edit, detail, link and unlink, including linked vehicles and audit history | High | Not Started | 2026-10-21 | 2026-10-22 | 3 |  |  |  | CRM-01/02/04/05/06/08/11; record observed results on Jira
Walk VIN prefill and Image Studio upload, enhance, delete and isolation; record outcomes | High | Not Started | 2026-10-22 | 2026-10-23 | 3 |  |  |  | EXT-01/08–10; VIN-01–04; IMG-01–05; screenshots and Jira findings
Walk ad editor states; record Ready and export behavior for each state | High | Not Started | 2026-10-23 | 2026-10-24 | 3 |  |  |  | AD-07/09/11/12
Walk assistant cards and fallback; record absence of costs and customer contacts | High | Not Started | 2026-10-26 | 2026-10-27 | 3 |  |  |  | AI-03/04
Inspect browser traffic across core and extension routes; record Gateway-only outcomes | High | Not Started | 2026-10-28 | 2026-10-29 | 3 |  |  |  | ARC-03; current extension routes
Resolve one prioritized UI issue or document rechecks; prepare owned demo steps and evidence | Normal | Not Started | 2026-10-30 | 2026-10-31 | 3 |  |  |  | Select Jira ID before starting; split work over 3 hours
Planned hours total |  |  |  |  | 30
Sprint 1: Oct 12–Nov 1, 2026. Ten tasks × 3 hours = 30 hours per member. Due dates are the day after the planned start.
Update actual dates, hours and status only after work occurs. Add Jira / evidence links to Notes. Split tasks over 3 hours and replan carryover.

## Jackson (Role B)
DealerOps Sprint 1 — Jackson Warga — AI and Platform
Task | Priority | Status | Planned start | Planned due | Planned hours | Actual start | Actual completion | Actual hours | Requirement and evidence notes
Review AI provider readiness and secret handling; record a setup checklist without secret values | High | Not Started | 2026-10-12 | 2026-10-13 | 3 |  |  |  | SEC-04; AI setup notes
Run a compliant ad through real AI and inspect notes separately from rule findings | High | Not Started | 2026-10-14 | 2026-10-15 | 3 |  |  |  | AI-01/02/05 (Should); AD-08; record returned state and screenshot
Run a hard-rule-miss ad; record that AI is skipped and the result is Blocked | High | Not Started | 2026-10-16 | 2026-10-17 | 3 |  |  |  | AD-03/07
Walk AI failure behavior; record that no failure produces Passed | High | Not Started | 2026-10-19 | 2026-10-20 | 3 |  |  |  | AI-02; AD-09
Change ad content after a pass; record Stale state and export denial | High | Not Started | 2026-10-21 | 2026-10-22 | 3 |  |  |  | AD-10/11/12
Walk self-registration, pending-account binding and all three sign-in identifiers; record outcomes | High | Not Started | 2026-10-22 | 2026-10-23 | 3 |  |  |  | EXT-05–07; AUTH-16–22; Jira pass/fail evidence per scenario
Ask scoped assistant questions; record permitted cards and fallback outcomes | High | Not Started | 2026-10-23 | 2026-10-24 | 3 |  |  |  | AI-03/04
Review ad and assistant contexts; record absence of costs and customer contact data | High | Not Started | 2026-10-26 | 2026-10-27 | 3 |  |  |  | AI-04; SEC-07
Update provider and startup notes against actual configuration; link reviewed changes | High | Not Started | 2026-10-28 | 2026-10-29 | 3 |  |  |  | README; ai-service notes
Update and publish separate Research and AI Logs in the team site; submit sprint AI evidence | Normal | Not Started | 2026-10-30 | 2026-10-31 | 3 |  |  |  | Research-Log.md; AI-Log.md; record real URL and member contributions
Planned hours total |  |  |  |  | 30
Sprint 1: Oct 12–Nov 1, 2026. Ten tasks × 3 hours = 30 hours per member. Due dates are the day after the planned start.
Update actual dates, hours and status only after work occurs. Add Jira / evidence links to Notes. Split tasks over 3 hours and replan carryover.

## Logan (Role C)
DealerOps Sprint 1 — Logan Jones — Gateway and Core
Task | Priority | Status | Planned start | Planned due | Planned hours | Actual start | Actual completion | Actual hours | Requirement and evidence notes
Review login, JWT and membership flows; record manual walkthrough steps | High | Not Started | 2026-10-12 | 2026-10-13 | 3 |  |  |  | AUTH-01/03/07/08/09/12; AUTH-16–22
Walk two-dealership and Admin denial scenarios; record status codes and outcomes | High | Not Started | 2026-10-14 | 2026-10-15 | 3 |  |  |  | AUTH-06/07/08/09; demo data prepared Oct 12; record denial status codes
Walk vehicle create, update and sale rules; attach observed API outcomes | High | Not Started | 2026-10-16 | 2026-10-17 | 3 |  |  |  | DMS-01/03/10/11
Walk customer and vehicle-link flows; record dealership-scope outcomes | High | Not Started | 2026-10-19 | 2026-10-20 | 3 |  |  |  | CRM-05/06/08/09
Review audit actor, action, time and changed-field summary with masked customer contacts | High | Not Started | 2026-10-21 | 2026-10-22 | 3 |  |  |  | AUD-01/02/03/05/06; AUD-04 (Should); record example outcomes
Walk lead follow-up and work-order rules across two dealerships, including costs and sale gate | High | Not Started | 2026-10-22 | 2026-10-23 | 3 |  |  |  | EXT-02–04; LEAD-01–09; WO-01–07; per-scenario outcomes and defects
Walk public and internal routes; record Gateway bypass denial and allowed public routes | High | Not Started | 2026-10-23 | 2026-10-24 | 3 |  |  |  | ARC-03; login/register/VIN exceptions
Compare core and extension API behavior with OpenAPI; list contract discrepancies | High | Not Started | 2026-10-26 | 2026-10-27 | 3 |  |  |  | ARC-06; dealer-platform/openapi.yaml
Review Terraform variables and deployment settings; record secret-handling findings | High | Not Started | 2026-10-28 | 2026-10-29 | 3 |  |  |  | ARC-07; SEC-03/04
Consolidate manual outcomes, blockers and deployment readiness; link evidence | Normal | Not Started | 2026-10-30 | 2026-10-31 | 3 |  |  |  | Select defects for carryover with owner and due date
Planned hours total |  |  |  |  | 30
Sprint 1: Oct 12–Nov 1, 2026. Ten tasks × 3 hours = 30 hours per member. Due dates are the day after the planned start.
Update actual dates, hours and status only after work occurs. Add Jira / evidence links to Notes. Split tasks over 3 hours and replan carryover.

## Yuandong (Lead)
DealerOps Sprint 1 — Yuandong Yang — Full Stack Lead
Task | Priority | Status | Planned start | Planned due | Planned hours | Actual start | Actual completion | Actual hours | Requirement and evidence notes
Seed two-dealership demo data and document repeatable setup before the first walkthrough | High | Not Started | 2026-10-12 | 2026-10-13 | 3 |  |  |  | AUTH-06/07; setup notes and demo records; no real customer data
Create Jira cards; request scope and NN-05 confirmation; record submission deadlines and backlog links | High | Not Started | 2026-10-14 | 2026-10-15 | 3 |  |  |  | IDs, owners, evidence fields; request student IDs; retain unconfirmed items as pending
Review and merge ready team pull requests; record requirement and review evidence | High | Not Started | 2026-10-16 | 2026-10-17 | 3 |  |  |  | List actual PR links; document blockers when no PR is ready
Fix one prioritized login or membership defect, or record acceptance rechecks | High | Not Started | 2026-10-19 | 2026-10-20 | 3 |  |  |  | Choose Jira ID first; link change and observed result; timebox 3 hours
Run Terraform validate and plan; record reviewed variables and apply/teardown checklist | High | Not Started | 2026-10-21 | 2026-10-22 | 3 |  |  |  | ARC-07; SEC-03/04; no deployment is implied
Fix one prioritized DMS or CRM defect, or record acceptance rechecks | High | Not Started | 2026-10-23 | 2026-10-24 | 3 |  |  |  | Choose Jira ID first; split remaining work; DMS/CRM requirements
Check all five main-branch workflows; record run links and any failed or missing run | High | Not Started | 2026-10-26 | 2026-10-27 | 3 |  |  |  | ARC-04; record actual results rather than assume success
Triage extension findings; fix one prioritized issue or record rechecks and carryover | High | Not Started | 2026-10-27 | 2026-10-28 | 3 |  |  |  | VIN/LEAD/WO/AUTH/IMG; explicit owner and due date per open issue
Fix one prioritized ad or assistant defect, or record acceptance rechecks | High | Not Started | 2026-10-28 | 2026-10-29 | 3 |  |  |  | Choose Jira ID first; AD-07/09/11/12; AI-03/04
Consolidate evidence and rehearse showcase; prepare report for actual sprint-close update | Normal | Not Started | 2026-10-30 | 2026-10-31 | 3 |  |  |  | Preparation Oct 30; close Nov 1; do not invent review feedback
Planned hours total |  |  |  |  | 30
Sprint 1: Oct 12–Nov 1, 2026. Ten tasks × 3 hours = 30 hours per member. Due dates are the day after the planned start.
Update actual dates, hours and status only after work occurs. Add Jira / evidence links to Notes. Split tasks over 3 hours and replan carryover.