Student Name: Team G2	Weight:	10%

Student ID:	Marks:	/17

# DealerOps Project Plan

## Background

DealerOps is a multi-tenant dealership back-office system with dealer management, customer records, advertising compliance, and a read-only AI assistant. As of October 8, 2026, the four applications (dealer-web, dealer-gateway, dealer-core, ai-service) and the shared API contract are implemented, and the stack was deployed once to Azure with Terraform, verified, and torn down to control cost. On the same day the team also delivered VIN decode, lead follow-up, reconditioning work orders, Image Studio, and self sign-up with sign-in by email, username, or phone; their manual acceptance starts in Sprint 1. This plan schedules the remaining manual acceptance, defect fixing, cloud redeployment, and classroom demonstration work for the approved course scope.

## Instructions

- This is a team submission.

- You will be provided time in class during week 4 to complete this assignment. However, you will likely need to do work outside of class as well.

- The submission should include a completed version of this template, along with a plan for sprint 1 using the provided spreadsheet.

- All tasks should be specific, measurable, and time-bound (SMART)

Table of Contents

DealerOps Project Plan	1

Background	1

Instructions	1

Overall Timeline	3

Minimum Viable Product (MVP) Backlog	3

Deliverables Outside of Minimum Viable Product	3

Project Management Methodology	4

Tool	4

Daily, Weekly, and Sprint Cadence	4

Sprint 1 Plan on a Page	5

Sprint 1 Goal	5

Sprint 1 Backlog	5

Sprint 1 Resource Plan	5

Sprint 1 Stakeholder Communication Plan	5

Sprint 2 Plan on a Page	6

Sprint 2 Goal	6

Sprint 2 Backlog	6

Sprint 2 Resource Plan	6

Sprint 2 Stakeholder Communication Plan	6

Sprint 3 Plan on a Page	7

Sprint 3 Goal	7

Sprint 3 Backlog	7

Sprint 3 Resource Plan	7

Sprint 3 Stakeholder Communication Plan	7

Sprint 1 Plan	8

Marking Criteria	9

# Overall Timeline

The execution phase runs for nine weeks in three three-week sprints, beginning October 12, 2026. Sprint 1 plans 30 hours per member (ten 3-hour tasks in Sampletasklist.xlsx); Sprints 2 and 3 plan 27 hours per member and are broken into tasks at each sprint planning.

| Phase | Dates (2026) | Weeks | Class hours per week | Total Class hours | Additional hours expected per week | Total Additional hours expected | Total hours per student |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | Oct 12-Nov 01 | 3 | 3 | 9 | 7 | 21 | 30 |
| Sprint 2 | Nov 02-Nov 22 | 3 | 3 | 9 | 6 | 18 | 27 |
| Sprint 3 | Nov 23-Dec 13 | 3 | 3 | 9 | 6 | 18 | 27 |
| Total |  | 9 |  | 27 |  | 57 | 84 |

# Minimum Viable Product (MVP) Backlog

Listed in the table below are our User Stories that have a Priority of “Must” (not “Should” or “Could”) in our overall Product Backlog (see Business Canvas document).

Collectively, these User Stories constitute the feature set required for a Minimum Viable Product for the solution we are proposing.

The User Story ID should be CONSISTENT with the numbering used in the Product Backlog.

| User Story ID | As a… | I want to be able to… | So that… |
| --- | --- | --- | --- |
| AUTH-01–05/10–12; SEC-01/02 | Platform admin | open a dealership and issue staff accounts | authorized staff can sign in |
| AUTH-06/07/08/09; SEC-05 | Dealer user | access my dealership's records | records stay isolated by dealership and role |
| DMS-01–03/05/06/08–12/14/15; NFR-01 | Dealer user | manage vehicle inventory and paired sales | vehicle rules and history stay accurate |
| CRM-01–09/11/12 | Dealer user | manage customers and eligible vehicle links | customer and vehicle history stays connected |
| AD-01–13 | Dealer user | check an ad and export a current pass as TXT | only reviewed public data is exported |
| AI-01/02 | Dealer user | receive a real AI review after hard rules pass and see a clear unavailable state on failure | the system never reports an AI failure as approval |
| AI-03/04 | Dealer user | ask read-only questions about dealership records | answers exclude other dealers and private details |
| AUD-01–03/05–07; SEC-07 | Dealer user | see who changed a vehicle or customer record and when | important business changes are traceable |
| ARC-01–06 | System operator | route browser requests through the gateway to the four applications | public access follows the approved service boundaries |
| ARC-07/SEC-03/SEC-04/NFR-08 | System operator | deploy with Terraform, HTTPS, CI/CD, and external secrets | the approved cloud demo can run safely |
| VIN-01–04 | Dealer user | decode a VIN and prefill a new vehicle without saving it | vehicle details are checked before entry |
| LEAD-01–05/07–09 | Dealer user | record leads with a stage, owner, follow-up date, and notes | sales follow-up stays within my dealership and is auditable |
| WO-01–06 | Dealer user | track reconditioning work orders and block a sale while work is open | repair costs and vehicle readiness stay accurate |
| IMG-01–05 | Dealer user | upload, enhance, and delete vehicle photos | listing images stay within my dealership |
| AUTH-16–21 | New staff member | register and sign in with my email, username, or phone and a password | the admin can bind my existing account to a dealership |

# Deliverables Outside of Minimum Viable Product

Listed in the table below are deliverables you must complete or update for each sprint. These deliverables are deliberately not included with the Minimum Viable Product Backlog (above) as they do not represent features of the product. When you plan for a sprint, ensure to allocate time to completing these deliverables.

| # | Deliverable | Description |
| --- | --- | --- |
| (1) | Updated Documentation | Update the business canvas, project plan, scope decisions, and setup notes at each sprint review. |
| (2) | Sprint Progress Report | Record completed stories, evidence, unfinished work, blockers, and next-sprint priorities once per sprint. |
| (3) | Solution Showcase | Demonstrate the working increment to the instructor or client once per sprint and record feedback. |

# Project Management Methodology

The team will use Scrum, as required by the course, with a prioritized Jira backlog and sprint board. GitHub repositories and Actions will hold the implementation, review history, and build or deployment workflows. A shared team space will hold the project plan, sprint reports, research log, AI log, and demo evidence. Scrum fits the three-week delivery cycle: the team can review working increments with stakeholders and adjust the next sprint without expanding the approved scope. We compared Scrum with Kanban and Waterfall before choosing. Kanban suits a continuous flow of work but has no sprint boundary to line up with the three course reviews. Waterfall assumes requirements are fixed up front, while our remaining work is driven by acceptance findings that change the defect backlog every week.

## Tool

The course uses an Agile approach and provides a tracking spreadsheet.

What additional methodologies and/or tools will you use to manage your project, and why?

Jira tracks the prioritized backlog, sprint owners, and blockers. One GitHub repository holds the four applications and the shared platform contract, with a separate GitHub Actions workflow per application, pull-request reviews, and CI/CD evidence. The team site holds decisions, research and AI logs, reports, and demo evidence. Terraform provisions Azure App Service and Static Web Apps for the approved scope.

## Daily, Weekly, and Sprint Cadence

Describe daily, weekly, and sprint use of the selected tools, including meeting agendas.

Daily check-in: 10 minutes at the start of each class, covering yesterday's outcome, today's Jira task, and blockers; each member writes one progress paragraph at the end of class. Weekly review: 30 minutes to check dependencies, workload, risks, open pull requests, and documentation. Week 2 of each sprint: a client meeting whose minutes record decisions, owners, and due dates. Each three-week sprint (our monthly cadence): planning at the start; a showcase where every member presents their own evidence, the status report, and a short retrospective with assigned improvement actions at the end. Research and AI use are logged in the separate team-site logs when they happen.

# Sprint 1 Plan on a Page

## Sprint 1 Goal

What are we trying to accomplish?

By the end of Sprint 1, we want to have accomplished these things:

|  | Goal |
| --- | --- |
| 1 | Close the highest-priority end-to-end gaps in login, roles, and dealership isolation. |
| 2 | Manually verify core DMS and CRM workflows and the October 8 extensions (VIN decode, leads, work orders, self sign-up, Image Studio) against the approved fields and rules. |
| 3 | Manually verify ad-check and assistant behavior, including blocked, stale, and AI-unavailable states. |
| 4 | Resolve and record the highest-impact integration defects found during the checks. |
| 5 | Publish a Sprint 1 report and a repeatable evidence-backed demo script. |

## Sprint 1 Backlog

What product backlog stories will we complete?

To achieve the Sprint Goal, these stories must be completed:

The User Story ID should be CONSISTENT with the numbering used in the Product Backlog.

| User Story ID | As a… | I want to be able to… | So that… |
| --- | --- | --- | --- |
| AUTH-01/03/07/08/09/11/12 | Platform admin or dealer user | sign in and reach only the pages and records allowed by my role and membership | authorization and dealership isolation work end to end |
| DMS-01/03/05/07 (Should)/08/10/11/14 | Dealer user | create, edit, search, filter, inspect, and sell a vehicle using the required fields | vehicle and sale rules are enforced |
| CRM-01/02/04/05/06/08/11 | Dealer user | manage a customer and link or unlink an eligible vehicle | customer history stays correct and auditable |
| AD-07/09/11/12 | Dealer user | see blocked, stale, and unavailable outcomes | failed or outdated checks cannot be exported as passed |
| AI-03/04/05 (Should) | Dealer user | ask a dealership-scoped read-only question and see AI notes separately from rule findings | the answer respects data and privacy boundaries |
| AUD-01/02/03/05/06; AUD-04 (Should) | Dealer user | see who changed a vehicle or customer record, when, and which fields changed | changes are traceable without exposing customer contact values |
| VIN-01–04; LEAD-01–09; WO-01–07; AUTH-16–22; IMG-01–05 (LEAD-06, WO-07, AUTH-22 Should) | Dealer user or new staff member | use VIN decode, lead follow-up, work orders, self sign-up, and Image Studio as specified | the October 8 extensions pass manual acceptance across two dealerships |

## Sprint 1 Resource Plan

Who will do what to accomplish our goal?

| Team Member | What tasks the Team Member will commit to work on |
| --- | --- |
| Bedgel Fadhil Ndam Woukouo (Role A: web) | Own the five web routes and floating assistant review, role navigation, DMS/CRM/ad/assistant UI walkthroughs, the gateway-only browser traffic check, and the demo script. On October 22, walk VIN prefill and Image Studio upload, enhance, delete, and isolation. |
| Jackson Warga (Role B: AI and platform) | Own real AI provider setup review, ad-check and assistant walkthroughs, privacy boundary review, AI/research logs, and AI setup notes. On October 22, walk self sign-up, pending-account binding, and sign-in by email, username, and phone. |
| Logan Jones (Role C: gateway and core) | Own login/membership and tenant checks, DMS/CRM/audit walkthroughs, gateway routing, API contract review, and release readiness notes. On October 22, walk lead follow-up and work-order rules, including the sale gate, across two dealerships. |
| Yuandong Yang / Robin (full-stack lead) | Triage walkthrough defects in Jira with requirement IDs, fix confirmed defects across web, gateway, core, and ai-service, review and merge pull requests, prepare two-dealership demo data, and run Terraform validate/plan with a teardown checklist. Request written confirmation of the scope baseline and the NN-05 containerization exception, and fix extension defects on October 27. |

## Sprint 1 Stakeholder Communication Plan

How will we communicate with our stakeholders?

| Stakeholder | What do they need to know | Frequency |
| --- | --- | --- |
| Instructor | Sprint goal, working increment, evidence, blockers, and scope decisions | Sprint review; weekly update if blocked |
| Client or dealership representative | Whether the user workflows and compliance outcomes match the approved scope | Week 2 meeting; sprint showcase |
| Project team | Daily progress, dependencies, changed priorities, and risks | Daily check-in and weekly review |

# Sprint 2 Plan on a Page

## Sprint 2 Goal

What are we trying to accomplish?

By the end of Sprint 2, we want to have accomplished these things:

|  | Goal |
| --- | --- |
| 1 | Recreate the Azure environment from the reviewed Terraform configuration and confirm cost-aware teardown steps. |
| 2 | Deploy the four applications and verify the public web and gateway entry points over HTTPS. |
| 3 | Run the two-dealership classroom scenarios for roles, isolation, DMS, CRM, and audit. |
| 4 | Demonstrate ad compliance and the read-only assistant with the agreed real-AI provider. |
| 5 | Capture review evidence, resolve deployment blockers, and publish the Sprint 2 report. |

## Sprint 2 Backlog

What product backlog stories will we complete?

To achieve the Sprint Goal, these stories must be completed to achieve the sprint goal:

The User Story ID should be CONSISTENT with the numbering used in the Product Backlog.

| User Story ID | As a… | I want to be able to… | So that… |
| --- | --- | --- | --- |
| ARC-07/SEC-03/SEC-04; NFR-04 (Should) | System operator | provision and deploy the apps with Terraform, HTTPS, CI/CD, externalized secrets, and the agreed database backup retention | the cloud demo can be repeated safely and recovery expectations are clear |
| ARC-03/NFR-08 | Instructor | open the published web app and gateway and identify the deployed versions | the release is accessible and traceable |
| AUTH-06/07/08/09; DMS-03; CRM-09 | Dealer user or platform admin | complete the two-dealership and role-separation scenarios | cross-dealership and role boundaries are demonstrated |
| AD-07/09/11/12/13; AI-01/02 | Dealer user | see a real check, a blocked case, a stale case, and an AI failure safely | only a current passed ad can be exported |
| AI-03/04 | Dealer user | ask a question and receive only permitted dealership information | the assistant remains useful and read-only |
| VIN-01–04; LEAD-01–09; WO-01–07; AUTH-16–22; IMG-01–05 | Dealer user or new staff member | repeat the extension scenarios on the deployed release | the extensions work in the cloud, not only locally |
| SEC-06; LEAD-06; WO-07 (all Should) | Dealer user | see that ad text cannot change the AI verdict, filter overdue leads, and see open work-order counts | AI review stays safe and follow-up work stays visible |

## Sprint 2 Resource Plan

Who will do what to accomplish our goal?

| Team Member | What tasks the Team Member will commit to work on |
| --- | --- |
| Bedgel Fadhil Ndam Woukouo (Role A: web) | Own production web deployment, page/version evidence, browser walkthroughs, and UI fixes from the two-dealership demo. Include the extension UI flows. |
| Jackson Warga (Role B: AI and platform) | Own AI service deployment settings, real-model demo cases, AI failure handling evidence, and provider/setup documentation. Include the SEC-06 prompt-injection cases. |
| Logan Jones (Role C: gateway and core) | Own gateway/core configuration review, HTTPS and health checks, cross-dealership API evidence, and the teardown checklist. Include the extension API and tenant checks. |
| Yuandong Yang / Robin (full-stack lead) | Own the Terraform apply and app release with a second-person approval, fix deployment defects across all services, and record release evidence. |

## Sprint 2 Stakeholder Communication Plan

How will we communicate with our stakeholders?

| Stakeholder | What do they need to know | Frequency |
| --- | --- | --- |
| Instructor | Cloud availability, required demo cases, evidence, and unresolved risks | Weekly; sprint showcase |
| Client or dealership representative | Whether the cloud increment supports the approved workflows | Week 2 meeting; sprint showcase |
| Project team | Deployment window, cost controls, release state, and blockers | Before and after each deployment; daily check-in |

# Sprint 3 Plan on a Page

## Sprint 3 Goal

What are we trying to accomplish?

By the end of Sprint 3 we want to have accomplished these things:

|  | Goal |
| --- | --- |
| 1 | Complete the classroom acceptance walkthrough for the approved scope without expanding product features. |
| 2 | Resolve critical issues from Sprint 2 and repeat affected manual scenarios. |
| 3 | Finalize project documentation, research and AI logs, and all three sprint reports. |
| 4 | Rehearse the end-to-end showcase and confirm the environment can be safely stopped afterward. |
| 5 | Present the final solution and record stakeholder feedback and known limitations. |

## Sprint 3 Backlog

What product backlog stories will we complete?

To achieve the Sprint Goal, these stories must be completed to achieve the sprint goal:

The User Story ID should be CONSISTENT with the numbering used in the Product Backlog.

| User Story ID | As a… | I want to be able to… | So that… |
| --- | --- | --- | --- |
| ARC-07/SEC-03/SEC-04; NFR-04 (Should) | Project team | deploy or stop the approved cloud environment using the documented runbook and confirm backup-retention settings | the final demonstration is available, database recovery expectations are clear, and avoidable resources do not remain running |
| AUTH-01/07/08; DMS-10/11; CRM-05/08 | Instructor | see role, isolation, paired-sale, sold-lock, and vehicle-link scenarios | the required business controls are demonstrated |
| AD-07/09/11/12/13; AI-01/02/03/04 | Instructor | see compliance and assistant scenarios with safe AI failure behavior | the AI features meet the approved acceptance conditions |
| AUD-01/02/03/05/06 | Dealer user | review the actor, action, time, and history for business changes | the audit trail is visible and useful |
| NFR-08; project deliverables | Project team | present version evidence, reports, and final documentation | the course handoff is complete and traceable |
| VIN-01–04; LEAD-01–09; WO-01–07; AUTH-16–22; IMG-01–05 | Instructor | see the accepted extension workflows and their known limitations | the final demonstration covers the full delivered scope |
| CRM-10; DMS-13 (both Should) | Dealer user | move between linked vehicle and customer details and get a conflict message on stale edits | navigation is quick and concurrent edits are not lost |

## Sprint 3 Resource Plan

Who will do what to accomplish our goal?

| Team Member | Significant tasks Team Member will commit to work on |
| --- | --- |
| Bedgel Fadhil Ndam Woukouo (Role A: web) | Lead the final role-based UI walkthrough, fix agreed UI blockers, prepare and present the web demo, and archive screenshots. Include the extension UI flows. |
| Jackson Warga (Role B: AI and platform) | Lead the final real-AI and assistant walkthrough, complete AI/research logs, and document provider limitations. Include the extension privacy boundaries. |
| Logan Jones (Role C: gateway and core) | Lead the final isolation and API walkthrough, verify deployment/teardown notes, and consolidate release evidence. Include the extension API and tenant checks. |
| Yuandong Yang / Robin (full-stack lead) | Fix critical defects from Sprint 2 across all services after the feature freeze, run the final redeploy and teardown, and consolidate release evidence with Logan Jones. |

## Sprint 3 Stakeholder Communication Plan

How will we communicate with our stakeholders?

| Stakeholder | What do they need to know | Frequency |
| --- | --- | --- |
| Instructor | Final acceptance evidence, known limitations, and completed course deliverables | Final showcase and handoff |
| Client or dealership representative | Final workflows, compliance outcomes, and feedback items | Week 2 meeting; final showcase |
| Project team | Final issue status, demo ownership, and teardown completion | Weekly; final rehearsal |

## Sprint 1 Plan

Using the chosen project methodology and any relevant tools, plan out your first sprint.

- Use the spreadsheet provided.

- All team members should have 27-36 hours of tasks planned.

- No task should be longer than 3 hours. If so, break it into sub-tasks.

- Please refer to the rubric for details.

- Each group should also maintain a Research Log and an AI Log throughout the sprint.  Please put this in a separate document in your teams’ site

Our Sprint 1 task list is in Sampletasklist.xlsx: one sheet per member with ten 3-hour tasks each (30 hours per member, 120 team hours). Each task has a start date, a next-day due date, the requirement IDs it covers, and the evidence it produces. Weekly loads are 9, 12, and 9 hours for Bedgel, Jackson, and Logan, and 9, 9, and 12 hours for Robin.

Dependencies: Robin seeds the two-dealership demo data on October 12, before the first isolation walkthrough on October 14. Each defect fix follows the walkthroughs that report it: login and membership on October 19, DMS and CRM on October 23, extensions on October 27, and ad check and assistant on October 28.

The Research Log and AI Log are kept as separate documents (project-plan/Research-Log.md and project-plan/AI-Log.md). Jackson publishes them to the team site by October 31; every member adds their own dated entries.

Research Log:

| Team Member | Topic | Source | URL | Date |
| --- | --- | --- | --- | --- |

AI Log

| Team Member | AI Tool | Purpose | Date |
| --- | --- | --- | --- |

# Marking Criteria

| Criteria | 4 | 3 | 2 | 0 |
| --- | --- | --- | --- | --- |
| Minimum Viable Product | The stories chosen from the product backlog form a clear minimum viable product that solves a compelling problem. Enough stories are chosen for adequate complexity, however few enough that the goal is clear. | The stories chosen from the product backlog form a minimum viable product that solves a problem. Enough stories are chosen for adequate complexity, however few enough that the goal is reasonably clear. | The stories chosen from the product backlog could form a minimum viable product that solves a problem. | There is no minimum viable product, or the stories chosen could not form a minimum viable product. |
| Project Management Methodology | Adequate research was put into choosing the project methodology, and there are clear expectations set for how procedures will be managed on a daily, weekly, and monthly basis. | Adequate research was put into choosing the project methodology, and there are expectations set for how procedures will be managed on a daily, weekly, and monthly basis. | A project methodology was chosen, and how the project will be managed is described, although clarification may be required. | A project methodology was not chosen, or it is unclear how the project will be managed. |
| Criteria | 3 | 2.25 | 1.75 | 0 |
| Sprint Plans | There is clear thought behind the stories the team intends to complete each sprint, and a mixture of must do and should do items for each sprint. Each team member has a number of key objectives. It is very clear who the stakeholders involved with each sprint are and how they will be communicated with. | There is thought behind the stories the team intends to complete each sprint, and a mixture of must do and should do items for each sprint. Each team member has a number of key objectives. It is clear who the stakeholders involved with each sprint are and how they will be communicated with. | There is thought behind the stories the team intends to complete each sprint. Most team members have a number of key objectives. Most stakeholders involved with each sprint are listed. | The sprint planning is unclear, not all members have stories assigned, or stakeholders are not correctly identified. |
| Criteria | 6 | 4.5 | 3 | 0 |
| Plan for Upcoming Sprint | Using the proposed project methodology, the team has planned tasks that will ensure each team member has at least 25-30 hours of work for the next sprint. Tasks are written in a SMART format. Larger tasks are broken down into smaller sub-tasks. It is clear what members plan to do on a week by week basis. | Using the proposed project methodology, the team has planned tasks that will ensure each team member has at least 25 hours of work for the sprint ahead. Tasks are written in a SMART format. Larger tasks are broken down into smaller sub-tasks. It is clear what members plan to do during the next sprint. | Using the proposed project methodology, the team has planned tasks that will ensure each team member has at least 20 hours of work for the next sprint. | A plan was not completing using the chosen methodology, or there is less than 20 hours per team member for the next sprint. |