## Slide 1: DealerOps — Sprint 1 Review
STATUS REPORT 2
Multi-tenant dealership operations platform · Progress, architecture and milestones
Capstone Group 2 (Team G2)
Yuandong Yang · Bedgel Fadhil Ndam Woukouo · Jackson Warga · Logan Jones
PROJ-309-SDA · Fall 2026 Capstone Project · 23 October 2026
Notes: Sprint 1 ran 12 October to 1 November. This review covers progress, the architectural changes made during the sprint, milestone status, and what we will demonstrate live.

## Slide 2: Where the project stands
Feature code is complete against the agreed scope; the sprint now closes on acceptance evidence and polish.
3 + 1
Core modules — DMS, CRM and ad compliance on one data set, plus the AI assistant
4
Independently deployable services: web, Gateway, Core and a stateless AI service
353
End-to-end API and UI cases passing on a private stack (22 October)
100%
Audited writes — every sign-in and every change records who, what, when and where
Sprint 1 in one line
Delivered: the stack moved onto .NET 10 + React 19 + MySQL 8, seven previously excluded requirements were implemented, the full delivery-extension set shipped (payments, bill of sale, dashboard, reports, buyer site, manager and staff roles, finance-grade audit), and Azure deployment became one command.
Behind plan: per-member acceptance walkthroughs, an evidence link on each Jira card, and publication of the research and AI logs.
Therefore: Sprint 2 is a hardening sprint — defect hunting, interface refinement and demonstration evidence, not new features.
Notes: Headline: the build is effectively finished. What is behind is project-management evidence, not functionality.

## Slide 3: What shipped in Sprint 1
Three streams of work, all merged to main between 12 and 23 October.
1
Reopened requirements
Seven requirements moved from “Won’t” to delivered: DMS-17, CRM-14, CRM-15, AD-15, AD-16 and NFR-07; AUTH-19 superseded.
Soft delete that keeps sales and audit history, the sales-funnel report, an admin-editable OMVIC rule set, labelled simulated publishing, and Gateway rate limits.
Each item carries its own evidence record.
2
Delivery extensions
Optional vehicle fields, payment ledger and printable bill of sale.
KPI dashboard, lead stage history and workshop settlement reporting.
Public buyer site turning each inquiry into a sales lead, plus a disclaimer page.
Dealership manager and staff roles, and audit held to a finance standard.
3
Platform and delivery
One-command Azure release from a clean, pushed checkout.
Local database published to the cloud with an automatic backup taken first.
Ten browser defects found, fixed and re-checked in a single day.
Scope reconciled against the client’s own documents.
Notes: Stream one closes requirement gaps, stream two is the client scope expansion of 21 October, stream three is delivery infrastructure and quality.

## Slide 4: Delivered product scope
Every module below is implemented and runnable today — this is what the live demo draws from.
Inventory · DMS
Eight specified fields, NHTSA VIN decode, sale recording with sold-field lock, soft delete that keeps history.
Customers · CRM
Required contact fields, one vehicle to one customer, linked vehicles and leads in the customer drawer.
Leads and reports
Five-stage pipeline with follow-up dates and append-only notes; funnel, sales and workshop reports; KPI dashboard.
Reconditioning and photos
Work orders whose completion cost rolls into repair cost and blocks a sale while open; Image Studio with enhancement presets.
Payments and bill of sale
Ledger of payments taken at the dealership, balance due, and a printable bill of sale template.
Ads, AI and buyer site
OMVIC checklist plus a real AI review, Ready and TXT export gating, and a public buyer site fed only by passed ads.
Notes: Six module groups. The demo walks the vehicle lifecycle across most of them in one story.

## Slide 5: Architectural updates
PART TWO
What changed in the system design during Sprint 1, and why.

## Slide 6: Four services, one public entry point
The browser talks to the Gateway only. Core owns every business rule and the single database; the AI service holds no data.
dealer-web
React 19 SPA
dealer-gateway
JWT · CORS · rate limits
dealer-core
Business rules · tenancy · audit
ai-service
Stateless model access
HTTPS
X-Dealer-Internal
MySQL 8 · dealer_core
Blocked: the browser can never reach Core, the AI service or the database directly
Figure 1 · Allowed request path in blue; the dashed red path must fail.
Notes: Architecture is unchanged in shape since Sprint 0; what changed inside it is the role model, the audit subsystem and the public buyer-site routes.

## Slide 7: Key architecture decisions
Each decision is recorded with its reason, so later changes argue against the reason rather than the choice.
Decision | Reason
One MySQL database for DMS, CRM and ads | The specification requires the three modules to work on the same dealership. One transaction can lock sale fields, invalidate an ad check and write the audit row together.
Synchronous REST, no message bus | No requirement needs asynchronous work; a queue would add an outbox, retries and failure modes without a business benefit.
Fixed rules run before the AI | A deterministic hard block is cheaper and explainable, and guarantees the model can never approve an ad the checklist already rejected.
Stateless AI service | The model provider is swapped by configuration, and AI never sees the database or another tenant.
Gateway as the only public origin | One place for CORS, token validation and rate limits; Core and the AI service stay private.
Terraform and App Service instead of containers | Recorded as decision NN-05. Services deploy as .NET 10 app packages with secrets resolved from Key Vault.
Notes: The last row is the one architectural change that still needs an instructor decision.

## Slide 8: Technology stack
The active stack after the Sprint 1 consolidation. The retired Java and Vue implementations are no longer part of delivery.
Layer | Technology | Notes
Frontend | React 19, TypeScript, Vite, React Router, Zustand | One HTTP client pointed at the Gateway URL from configuration
Gateway | .NET 10 / ASP.NET Core with YARP | Reverse proxy, JWT validation, rate limiting, health aggregation
Core service | .NET 10 / ASP.NET Core, EF Core | Grouped by business area: vehicle, customer, lead, work order, photo, payment, listing, compliance, audit
AI service | .NET 10 / ASP.NET Core | Provider, model and key come from configuration; no database access
Database | MySQL 8 (Azure Database for MySQL Flexible Server) | TLS required in the cloud; 7-day automatic backups
Identity | Local password (BCrypt), Google ID token, Firebase Auth | DealerOps always issues its own JWT; providers never grant roles or dealerships
Infrastructure | Terraform, Azure Linux App Service, Key Vault, App Insights | No containers; services deploy as .NET 10 app packages
CI | GitHub Actions | One workflow per service plus Terraform validate, on every pull request and on main
Notes: Consolidating onto one stack was the largest single change of the sprint.

## Slide 9: New this sprint: manager and staff separation
Authentication still issues only two token roles. The dealership level — manager or staff — is read from the membership on every call.
Platform Admin
Opens dealerships, creates and binds accounts, resets passwords.
Promotes and demotes managers; edits the global OMVIC rules.
Reads the platform audit log.
Receives 403 on every business endpoint — never sees dealership data.
Dealership Manager
Everything staff can do.
Team page and join-request inbox; removes staff; edits the dealership profile.
Reads and corrects the payment ledger.
Reads all audit data of the dealership.
Dealership Staff
Full read and write on daily business data: DMS, CRM, leads, ads, work orders, photos, assistant.
May record a payment, but cannot see or change the ledger.
Sees no audit data at all.
Tenancy is always derived on the server. Core loads the signed-in user’s single active membership and filters every query by that dealership. A dealerId sent by the browser is ignored; another dealership’s record returns 404, so a response never reveals that it exists.
Notes: The manager/staff split is the main permission change of the sprint: money oversight and audit visibility sit with the manager.

## Slide 10: Ad compliance: fixed rules before the AI
A deterministic OMVIC rule engine runs first. The model only adds advisory notes and can never turn a blocked ad into a passed one.
Run check
Staff submit the ad with its version
Guard
Tenant and optimistic-lock checks
Fixed OMVIC rules
Ad text, public vehicle fields, dealer profile
Any BLOCK?
Yes → saved BLOCKED, model not called
AI review
15-second budget through the AI service
Persist
Success → PASSED. Failure → AI_UNAVAILABLE
Check states shown to the user
PASSED
Rules passed and the AI review succeeded for this ad version
Ready and TXT export allowed
BLOCKED
A hard rule failed; the model was never called
Export refused
NEEDS AI
No check yet, or the ad changed after a blocked or unavailable result
Export refused
STALE
Was passed, but the ad text or the vehicle condition changed since
Export refused
AI UNAVAILABLE
Rules passed but the model failed or timed out — never shown as a pass
Export refused
Notes: Admin rule changes mark every existing check stale, so ads are rechecked under the new rule set.

## Slide 11: Deployment and operations
The release path became one command during this sprint, with the safety rails that earlier failures showed were needed.
Azure resource group, created by Terraform
App Service plan (Linux)
Four Linux web apps: the built SPA, Gateway, Core and the AI service as .NET 10 packages.
MySQL Flexible Server
Database dealer_core, TLS required, firewall limited to Azure and named operators, 7-day backups.
Key Vault + managed identity
Internal token, database password, JWT signing secret, AI key and admin password — no app setting holds a secret value.
Log Analytics + App Insights
Logs and telemetry for all four services; the Gateway aggregates downstream health and release times.
One release command
./deploy/deploy.sh --apply --seed
Refuses to run unless the checkout matches its pushed upstream, so every build is reproducible.
Applies Terraform, publishes the three .NET apps and the SPA built against the Gateway URL, retrying each upload.
Waits for the health checks, then verifies the result through the Gateway.
--seed publishes the local demo database: it backs up the Azure rows first, imports in one transaction and restarts Core.
A backup file restores the previous data; point-in-time restore covers a 7-day window.
Notes: Two impediments drove these rails: Azure state drift after a portal deletion, and Kudu refusing the first zip upload.

## Slide 12: Milestone tracking
PART THREE
Where each planned milestone stands against the three-sprint schedule.

## Slide 13: Milestones against the plan
Three sprints run 12 October to 13 December. Product scope is ahead of schedule; acceptance evidence is the item that is behind.
Milestone | Planned | Status at 23 October
Four services build independently; the two JWT roles defined | Sprint 1 | Done — plus the manager and staff membership level added this sprint
Running on Azure with no secret in source control | Sprint 2 | Done early — one-command release, Key Vault and managed identity
Two-dealership isolation, CRM linking, all three ad types, export, audit | Sprint 3 | Done early — including gated export and finance-grade audit
Client and delivery extensions: leads, work orders, Image Studio, buyer site, payments, dashboard, roles | Extensions | Done — scope reconciled with the client on 21 October
Per-member manual acceptance walkthroughs | Sprint 1 | Behind — scheduled 24–28 October, before sprint close
Jira backlog level with the delivered state | Sprint 1 | Done — every previously open KAN issue closed out on 23 October; an evidence link per card is carried to Sprint 2
Research and AI logs published; instructor acknowledgement of the scope baseline | Sprint 1 | Open — the NN-05 hosting decision itself is documented, corrected 19 October
Live two-dealership demo on the deployed environment | Sprint 2 | Rehearsal scheduled before the class demo
Notes: Read this as: construction finished early, governance evidence is the remaining debt.

## Slide 14: Quality evidence this sprint
A manual browser pass found defects the automated suite could not, because the existing checks read text instead of exercising the control.
10
Defects found in the 20 October browser walkthrough — all fixed and re-checked the same day
353
Playwright API and UI cases passing on a private stack with its own database (22 October)
5
GitHub Actions workflows building every service and validating Terraform on each pull request
What the defect cycle taught us
One defect made an admin control unclickable, yet the existing specs passed because they only read its label text. Coverage that asserts text rather than interaction gives false confidence.
A rule change was bumping the edit version of every ad, so a user with an ad open hit a conflict nobody had caused. Found only by having two screens open at once.
Both are now part of the walkthrough script, which is what the remaining acceptance work follows.
Notes: Use this to justify why the remaining sprint time goes to manual acceptance rather than more features.

## Slide 15: What we will demonstrate live
Six acceptance scripts, run on two dealerships with real demo data. Feature code is complete, so this is a finished build rather than a partial prototype.
1
The admin opens two dealerships and binds one person to each.
2
Dealership A records a vehicle and a customer and links them; dealership B cannot see either.
3
The admin calling the vehicle API is rejected.
4
A missing price, and a finance ad without APR, are blocked without calling the AI.
5
Real ad text goes through a real AI model once, and the missing items are identified.
6
After a price change the old check cannot be used to export, and the vehicle leaves the buyer site.
Plus the extension flow end to end: write an ad, check it, mark it ready, find it on the public buyer site, send an inquiry that becomes a lead, then sell the vehicle and watch it leave the site.
Notes: Minimum requirement is 50% of core features; all core modules are demonstrable.

## Slide 16: Limitations and what Sprint 2 carries
Where a feature needs a commercial agreement we do not have, the system offers a labelled alternative and says so on screen.
Stated limitations
Marketplace publishing
Simulated and labelled — needs a partner agreement and dealer API credentials. The buyer site is the real public channel.
Card payment processing
Not built — needs a merchant account and PCI scope. The ledger records payments taken at the dealership.
Document OCR, message queue, second database
Not built — no requirement needs them, and each adds failure modes.
Bill of sale
A printable template, not a lawyer-reviewed contract.
Production deployment
CI builds and validates; the release is run by an operator because CI holds no Azure credential.
Sprint 2 — a hardening sprint
Ownership by area rather than by hours: each member takes a defect-hunting and interface-review area and merges their own fixes.
Interface refinement against one written checklist — link style, icons, theme colours, empty states, error wording, loading and disabled states.
Requirement evidence mirrored onto the Jira board, not only the repository.
Actual dates and hours recorded weekly instead of at sprint close.
Research log and AI log published; scope baseline and NN-05 confirmed.
Live demo rehearsed on the deployed environment with the two-dealership data set.
Notes: The honest message: no new features are planned. The remaining risk is evidence and polish, not functionality.

## Slide 17: Questions, then the live demo
Where the detail lives
Scope and errata — design/SCOPE-BASELINE.md · Requirement IDs — requirements/DealerOps-Requirements.md
Architecture — design/07-Azure-Microservices-Architecture.md · API contract — design/14-Backend-API-Contract.md
Acceptance — design/16-Acceptance-and-Test.md · Deployment — deploy/README.md
Full system design briefing — design/presentation/DealerOps-System-Design.html
DealerOps · Capstone Group 2 (Team G2) · Sprint 1 review, 2026
Notes: Hand over to the live demo on the deployed environment.